## Product Backlog Week 1 Day 3
ID | Theme | User Story | Notes | Priority | Status |  | Task | User Story ID
1 | Concept | As an user, I want to have specifically formulated questions that indicate what this program will be able to answer, so that I can get a relative idea of what the capabilities of this program are. | Questions are to be taken from the user's perspective. "How many parking meters are there in Rotterdam?" indicates that the program is able to answer this question. | M | D |  | - Make 5 questions (ND) - Choose a topic (D) | 1
2 | Data | As a developer, I want to have verified data sources such as government-issued spreadsheets, so that I can create an application that can read this data and present it to users without having to question the credibility of the source | use sources such as http://rotterdamopendata.nl/dataset | M | D |  | - Find at least 2 datasources (D) | 2
3 | Structure | As a developer, I want to have a conceptual data model, so that I can use this as a reference when building the physical data model. |  | M | D |  | - Design general concept of the application (ND) - Create an ERD (ND) | 3
4 | Data | As a developer, I want to have a data parser, so that I can turn spreadsheets into SQL queries without doing everything manually. | a parser reads a spreadsheet's raw text, and in turns converts that to proper SQL queries | S | D | ND | -Find out how to read raw spreadsheet text -Turn the text into proper SQL queries | 4
5 | GUI | As a user, I want to be able to see the requested information on a map, so it's easier to get the information that I want. | Database contains GPS coordinates, use these to display everything accurately (see Google Maps) | M | D |  | -Figure out how to display info on a map -Draw relevant info on the map | 5
6 | GUI | As a user, I want to be able to navigate through the map by moving it around, constantly having the data updated so that the map stays clean. |  | M | D |  | -Make the map draggable -Make displayed info move along with the map | 6
7 | GUI | As a user I want to be able to enter a location and have the program pan to that specific location. |  | S | D | ND | -Make the map pan to a given area | 7
8 | Data | As a developer I want all relevant information inside a database, so it's easier to fetch the required data. |  | M | D |  | -Put all relevant info inside a database | 8
9 | GUI | As a user I want to be able to select the info that I want to see from a menu, instead of getting every possible thing thrown at me at once, so that I have a clear view of what I want to see. |  | S | ND |  | -Make a selection menu -Hide/display certain blips based on what's selected | 9
10 | GUI | As a user I want to let the application use my current location so that I can immediately see what's going on in my neighborhood |  | C | ND | ND | -Retrieve a user's current gps location -Make the map pan to this location | 10
11 | Data | As a user I want to be able to save an instance of the map as a file, so that I can look at it later without having to open the program |  | C | ND |  | -Add save functionality | 11
12 | GUI | As a user I want to be able to print out the map, so that I can use this information while I'm not behind my computer |  | W | ND |  | -Add a print function (actual printer, not console) | 12
13 | Data | As a developer I want to be able to get all the relevant data from the database, so that I can display it on the screen |  | M | D | ND
14 | GUI | As a user I want to be able to see data represented by district, as well as by suburb, so that I get a more detailed representation of the data |  | S | ND
15 | GUI | As a user I want to be able to select what year's data is shown, so that I get a more detailed representation of the data |  | S | ND
16 | [5 empty] | ND
17
18

## Sprint 2 Backlog
ID | Theme | User Story | Notes | Priority | Status |  | Task | User Story ID
4 | Data | As a developer, I want to have a data parser, so that I can turn spreadsheets into SQL queries without doing everything manually. | a parser reads a spreadsheet's raw text, and in turns converts that to proper SQL queries | S | ND | ND | -Find out how to read raw spreadsheet text -Turn the text into proper SQL queries | 4
5 | GUI | As a user, I want to be able to see the requested information on a map, so it's easier to get the information that I want. | Database contains GPS coordinates, use these to display everything accurately (see Google Maps) | M | ND |  | -Figure out how to display info on a map -Draw relevant info on the map | 5
6 | GUI | As a user, I want to be able to navigate through the map by moving it around, constantly having the data updated so that the map stays clean. |  | M | ND |  | -Make the map draggable -Make displayed info move along with the map | 6
7 | GUI | As a user I want to be able to enter a location and have the program pan to that specific location. |  | S | ND | ND | -Make the map pan to a given area | 7
8 | Data | As a developer I want all relevant information inside a database, so it's easier to fetch the required data. |  | M | ND |  | -Put all relevant info inside a database -Add GUI to parser | 8
9 | GUI | As a user I want to be able to select the info that I want to see from a menu, instead of getting every possible thing thrown at me at once, so that I have a clear view of what I want to see. |  | M | ND |  | -Put all relevant info inside a database -Add GUI to parser | 9
ND
ND
ND

## Sprint 3 Backlog
User Stories | To-Do | Doing | Done | Done User stories
As a user I want to be able to select the info that I want to see from a menu, instead of getting every possible thing thrown at me at once, so that I have a clear view of what I want to see. | Add a drop-down selection where users can select the year that they want the info from | Add a drop-down selection where users can select the year that they want the info from | Make database accessible to project | As a developer, I want to have a data parser, so that I can turn spreadsheets into SQL queries without doing everything manually.
As a user I want to be able to see data represented by district, as well as by suburb, so that I get a more detailed representation of the data |  | Make buttons to select what kind of info you want to see | Make SQL queries to request data and return it to a function | As a developer I want to be able to get all the relevant data from the database, so that I can display it on the screen
As a user I want to be able to select what year's data is shown, so that I get a more detailed representation of the data |  | Add button that lets you select a specific area in Rotterdam, and have it pan the camera to that area | Make the parser able to execute SQL queries as soon as they are converted | As a developer I want all relevant information inside a database, so it's easier to fetch the required data.
Make a nice presentation